## Project Gantt Chart
[12 empty] | 2026-02-09 | [12 empty] | 2026-05-11 | [12 empty] | 2026-08-10 | [12 empty] | 2026-11-09
| Project Start Date: | 2026-01-26 | [5 empty] | 2026-01-05 |  |  |  | 2026-02-09 |  |  |  | 2026-03-09 |  |  |  |  | 2026-04-13 |  |  |  | 2026-05-11 |  |  |  | 2026-06-08 |  |  |  |  | 2026-07-13 |  |  |  | 2026-08-10 |  |  |  |  | 2026-09-14 |  |  |  | 2026-10-12 |  |  |  | 2026-11-09 |  |  |  |  | 2026-12-14
| Project Name: | Trend Setter |  |  |  |  | Week Starting: | time axis 2026-01-05 to 2026-12-28
# | Week | Project Plan | Start | End | Days | Status | % Done
1 | Week 1: Jan 26 - 30 | Use ideas from over break to create project idea. | 2026-01-01 | 2026-01-30 | 22 | Complete | 100% | bar: 2026-01-05 to 2026-01-26
2 |  | Get book for class. | 2026-01-26 | 2026-01-30 | 5 | Complete | 100% | bar: 2026-01-05 to 2026-01-26
3 |  | Meet with both Dr. Dunbar and BMVP about project idea and steps moving forward. | 2026-01-26 | 2026-01-30 | 5 | Complete | 100% | bar: 2026-01-26
4 |  | Make sure I am able to login to WinSCP and have materials ready to start project. | 2026-01-26 | 2026-01-30 | 5 | Complete | 100% | bar: 2026-01-26 to 2026-02-02
5 |  | Start mythical man month chapters 1-3. | 2026-01-26 | 2026-01-30 | 5 | Complete | 100% | bar: 2026-01-26 to 2026-02-02
6 | Week 2: Feb 2 - 6 | Solve computer difficulties. | 2026-02-02 | 2026-02-06 | 5 | Complete | 100% | bar: 2026-01-26 to 2026-02-02
7 |  | Meet again with BMVP and Dr. Dunbar about progess update and more in-depth project analysis. | 2026-02-02 | 2026-02-06 | 5 | Complete | 100% | bar: 2026-02-02
8 |  | Start researching apis and begin preparing for mini-poster session. | 2026-02-02 | 2026-02-06 | 5 | Complete | 100% | bar: 2026-02-02
9 |  | Continue mythical man month chapters 4-7, 8-11 & prepare discussion for chapter 8. | 2026-02-02 | 2026-02-06 | 5 | Complete | 100% | bar: 2026-02-02
10 |  | Create start of webpage and include blog & upload resume and philosophy statement. | 2026-02-02 | 2026-02-06 | 5 | Complete | 100% | bar: 2026-02-02
11 | Week 3: Feb 9 - 13 | Prepare for mini-poster session this week & plan to take notes on other people's project as well a give feedback on them. | 2026-02-09 | 2026-02-13 | 5 | Complete | 100% | bar: 2026-02-09
12 |  | Start Pert or Gantt chart for Feb 19th. | 2026-02-09 | 2026-02-13 | 5 | Complete | 100% | bar: 2026-02-09
13 |  | Continue researching apis. | 2026-02-09 | 2026-02-13 | 5 | Complete | 100% | bar: 2026-02-09
14 |  | Continue mythical man month chapters 12-15 & prepare discussion for chapter 14. | 2026-02-09 | 2026-02-13 | 5 | Complete | 100% | bar: 2026-02-09
15 | Week 4: Feb 16 - 20 | Meet with BMVP about apis and my plan on incorporating them to my project. | 2026-02-16 | 2026-02-20 | 5 | Complete | 100% | bar: 2026-02-16
16 |  | Finish Gantt chart for Feb 19th. | 2026-02-16 | 2026-02-20 | 5 | Complete | 100% | bar: 2026-02-16
17 |  | Prepare for picture day on Feb 19th. | 2026-02-16 | 2026-02-20 | 5 | Complete | 100% | bar: 2026-02-16
18 |  | Continue mythical man month chapter 16. | 2026-02-16 | 2026-02-20 | 5 | Complete | 100% | bar: 2026-02-16
19 | Week 5: Feb 23 – Feb 27 | Cover HCI and plan for additional meetings with professors. | 2026-02-23 | 2026-02-27 | 5 | In Progress | 0% | bar: 2026-02-23
20 |  | HCI assignment due this week. | 2026-02-23 | 2026-02-27 | 5 | In Progress | 0% | bar: 2026-02-23
21 | Week 6: Mar 2 - 6 | Discuss professional/social discussion. | 2026-03-02 | 2026-03-06 | 5 | In Progress | 0% | bar: 2026-03-02
22 |  | Start looking at ACM code of ethics; case studies. | 2026-03-02 | 2026-03-06 | 5 | In Progress | 0% | bar: 2026-03-02
23 | Week 7: Mar 9 - 13 | Continue ethics of AI and Data Science. | 2026-03-09 | 2026-03-13 | 5 | In Progress | 0% | bar: 2026-03-09
24 | Spring Break: March 16 - 20 | Make additional preparations for project during this time such as additional storage for datasets. | 2026-03-16 | 2026-03-20 | 5 | In Progress | 0% | bar: 2026-03-16
25 | Week 8: Mar 23 - 27 | Discuss professional/social discussion. | 2026-03-23 | 2026-03-27 | 5 | In Progress | 0% | bar: 2026-03-23
26 |  | Advising Day | 2026-03-23 | 2026-03-27 | 5 | In Progress | 0% | bar: 2026-03-23
27 | Week 9: Mar 30 – Apr 3 (walk throughs and guest speakers?) | Advising Day | 2026-03-30 | 2026-04-03 | 5 | In Progress | 0% | bar: 2026-03-30
28 |  | Begin walkthroughs starting Thursday. | 2026-03-30 | 2026-04-03 | 5 | In Progress | 0% | bar: 2026-03-30
29 | Easter Break: Apr 3 - Apr 6 | General project work this break. | 2026-04-03 | 2026-04-06 | 2 | In Progress | 0% | bar: 2026-04-06
30 | Week 10: Apr 7 - 11 (walk throughs and guest speakers?) | Walkthroughs due Tues & Thurs. | 2026-04-07 | 2026-04-11 | 4 | In Progress | 0% | bar: 2026-04-13
31 | Week 11: Apr 14 – 18 | Abstract/Title Due | 2026-04-14 | 2026-04-18 | 4 | In Progress | 0% | bar: 2026-04-20
32 | Week 12: Apr 21 – 25 | Professional/Social Issue Discussion & Semester End Info and Documents. | 2026-04-21 | 2026-04-25 | 4 | In Progress | 0% | bar: 2026-04-27
33 | Week 13: Apr 28 – May 3 (Open Demos/Presentations Friday and Saturday) | Open Demos/Presentations. | 2026-04-28 | 2026-05-03 | 4 | In Progress | 0% | bar: 2026-05-04
34 | Week 14: May 5 - 9 | TBA Final project Defence. | 2026-05-05 | 2026-05-09 | 4 | In Progress | 0% | bar: 2026-05-11
35 | Week 15: May 12 - 16 (Finals week) (Sunday, May 11 is Mother’s Day!) | Website Due. | 2026-05-12 | 2026-05-26 | 11 | In Progress | 0% | bar: 2026-05-18
36 | Sunday, May 18 | Graduation! | 2026-05-18 | 2026-05-18 | 1 | In Progress | 0% | bar: 2026-05-25
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))